Chatbot Platform

Developer Task Breakdown

WhatsApp + Instagram  ·  Multi-tenant  ·  Rule-based
Version 1.0  ·  Generated 2026-06-03  ·  Stack: Django + DRF
Team: 3 developers (2 Senior + 1 Junior) + AI juniors

# How to use this document

These tasks follow the PIER workflow (Plan → Identify → Execute → Review) from CLAUDE.md. Every task runs full PIER; effort is proportionate to size. Tasks are grouped by developer, then by epic. Build [S] Shared work first, run [P] Parallel work concurrently, then complete [D] Dependent work.

Tags: [S] Shared = foundational, build first · [P] Parallel = independent · [D] Dependent = needs prior tasks.

Size: S ≈ ½ day · M ≈ 1 day · L ≈ 2 days.

AI-junior?: Yes = safe to delegate boilerplate to an AI sub-agent (human reviews) · Partial = scaffold with AI, human owns logic · NO = security or core logic; humans only, never delegated.

Golden Rule: AI never writes code until a human says “IMPLEMENT.” Security guardrails (CLAUDE.md §7) are never delegated.

# Execution order & dependencies

The 53 tasks are neither all independent nor a single chain. They form three layers: a foundational series that gates everything, three parallel streams that run concurrently, and a dependent finish that converges. Build [S] first, run [P] in parallel, then complete [D].

## Layer 1 — Foundation [S] (Dev 1, first)

Largely sequential. Blocks Dev 2 and Dev 3 until done — ship D1-05 + D1-12 early to unblock the others fast.

D1-01 init → D1-02 apps → D1-05 tenants → D1-07/08 models → D1-10 migrations

D1-05 → D1-06 encryption        D1-04 → D1-11 auth → D1-12 endpoint template

## Layer 2 — Three parallel streams [P] (run concurrently)

Independent of each other; each is an internal series.

Dev 1 engine : D1-13 → D1-14 → D1-15 → D1-17 → D1-19

Dev 2 webhook: D2-03 → D2-04 → D2-05 → D2-06 → D2-07 → D2-08 → D2-09

Dev 3 admin  : D3-01 → D3-02 → D3-03   and   D3-04 → D3-05

## Layer 3 — Dependent finish [D] (converges)

message sender : needs engine D1-19 + queue D2-08 + encryption D1-06

flow builder   : needs decision D-103/D1-20 + models D1-07

handoff        : needs engine-terminal D1-17 + email template D3-07

Instagram      : needs WA sender D2-12 + IG decision D2-15

## Critical path (longest chain)

Runs entirely through Dev 1's foundation, then the engine, then the sender, then Instagram — roughly 16 working days of strictly sequential work. Any slip here slips the whole project; Dev 1 is the bottleneck.

D1-01 → D1-02 → D1-07/08 → D1-13 → D1-14 → D1-15 → D1-17 → D1-19

→ D2-08 → D2-10 → D2-11 → D2-12 → D2-17 → D2-18

## Cross-developer handoffs (the scheduling risk)

Where one person waits on another. Everything traces back to Dev 1.

| Blocked task | Waits for | Direction |
| --- | --- | --- |
| D2-08 queue worker | D1-19 flow engine tested | Dev 2 ← Dev 1 |
| D2-10 message sender | D1-06 token encryption | Dev 2 ← Dev 1 |
| D3-01 admin CRUD | D1-05 model + D1-12 template | Dev 3 ← Dev 1 |
| D3-07 handoff email | D1-24 handoff backend | Dev 3 ← Dev 1 |
| D3-09 seed data | D1-10 migrations | Dev 3 ← Dev 1 |
| D2-17 Instagram | D2-12 WA sender + D2-15 IG decision | Dev 2 (internal) |
| D1-21 flow builder | D1-20 live-flow decision | Dev 1 (internal) |

Note: Dev 3 (Junior) is blocked earliest — nearly all their work needs Dev 1's models + endpoint template. In week 1, pair Dev 3 on the foundation or front-load non-code tasks (D3-11 runbook, UI mockups).

## Open-decision blockers (resolve in Week 0)

Each sits at the head of a chain; the chain stalls until it is decided.

| Decision | Blocks | Owner / when |
| --- | --- | --- |
| D-100 credential encryption | D1-06 → message sender | Dev 1 · Week 0 |
| D-101 Meta BSP selection | D2-01 → all WhatsApp work | PO + Dev 2 · Week 0 |
| D-102 Instagram capabilities | D2-15 → Instagram renderer | Dev 2 + PO · Week 0 |
| D-103 live-flow-edit behaviour | D1-20 → flow builder | Dev 1 · before builder |

## Suggested execution phases

| Phase | Focus | Tasks |
| --- | --- | --- |
| 0 — Week 0 | Resolve decisions + scaffold | D-100..103, D1-01..04, D2-01, D2-15 |
| 1 — Foundation | Models, encryption, auth | D1-05..12 |
| 2 — Parallel | Engine + webhook + admin | D1-13..19, D2-03..09, D3-01..06 |
| 3 — Convergent | Sender, builder, handoff, IG | D2-10..18, D1-20..24, D3-07..11 |

# Dev 1 — Architect + Senior

Scope. DB schema, credential encryption, multi-tenancy, flow engine, flow builder, auth scaffolding, handoff backend. Foundational work — most Shared [S] items live here and unblock Dev 2 & Dev 3.

24 tasks across 6 epics.

## Epic A — Project skeleton

### D1-01 · Init Django project + split settings

| Tag | [S] Shared |
| --- | --- |
| Size | S (~½ day) |
| Depends on | — |
| AI-junior? | Yes |
| Spec refs | architecture.md |

Description. Stand up the Django project with environment-driven, split settings so dev and prod configs never mix.

Technical notes

Create config/ project package with base/dev/prod settings modules.

Load secrets and DB/Redis URLs via django-environ from .env (never commit .env).

Provide .env.example with every key documented.

Acceptance criteria

☐  manage.py runserver boots using .env values.

☐  DEBUG, SECRET_KEY, DB and Redis come from environment, not hard-coded.

### D1-02 · Create 6 apps + register

| Tag | [S] Shared |
| --- | --- |
| Size | S (~½ day) |
| Depends on | D1-01 |
| AI-junior? | Yes |
| Spec refs | architecture.md |

Description. Create the module boundaries the whole team builds inside.

Technical notes

Apps: tenants, flows, conversations, channels, handoff, audit.

Add each to INSTALLED_APPS with an explicit AppConfig.

Acceptance criteria

☐  All six apps import cleanly.

☐  Project starts with the apps registered.

### D1-03 · Wire Celery + Redis

| Tag | [S] Shared |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D1-01 |
| AI-junior? | Yes |
| Spec refs | architecture.md C-02 |

Description. Set up the async backbone that decouples webhook receipt from flow execution.

Technical notes

config/celery.py with app autodiscovery.

Redis as broker/result backend (from env).

Add a trivial ping task to prove the wiring.

Acceptance criteria

☐  A Celery worker starts and runs the ping task end-to-end.

### D1-04 · Postgres connection

| Tag | [S] Shared |
| --- | --- |
| Size | S (~½ day) |
| Depends on | D1-01 |
| AI-junior? | Yes |
| Spec refs | architecture.md |

Description. Point the project at PostgreSQL.

Technical notes

DATABASES configured from env (psycopg).

Acceptance criteria

☐  manage.py migrate runs clean against a Postgres database.

## Epic B — Data models + migrations (C-08)

### D1-05 · tenants model + admin register

| Tag | [S] Shared |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D1-02 |
| AI-junior? | Partial |
| Spec refs | architecture.md §Data models |

Description. The central tenant record that everything else hangs off.

Technical notes

Fields: name, wa_phone_number, ig_account_id, handoff_enabled, handoff_email, greeting_message, closing_message, is_active, created_at (+ token fields added in D1-06).

Register in Django admin exposing config fields only (not raw tokens).

Acceptance criteria

☐  Product owner can create/edit a tenant's config in Django admin.

☐  is_active toggles a tenant on/off.

### D1-06 · Token encryption at rest

| Tag | [S] Shared |
| --- | --- |
| Size | L (~2 days) |
| Depends on | D1-05 |
| AI-junior? | NO (SEC-02) |
| Spec refs | CLAUDE.md §7, D-100 |

Description. Store each tenant's Meta access tokens encrypted; the encryption key lives outside the database. Resolves open decision D-100.

Technical notes

Use Fernet (cryptography) or equivalent for wa_access_token / ig_access_token.

Key sourced from env / secrets manager — never stored in the DB (SEC-02).

Ensure tokens never appear in __repr__, admin, logs, or error output.

Acceptance criteria

☐  Tokens are ciphertext at rest.

☐  Key is not present anywhere in the database.

☐  No code path logs a decrypted token.

☐  decisions.md D-100 marked DECIDED with the chosen mechanism.

### D1-07 · flow_steps + flow_options models

| Tag | [S] Shared |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D1-02 |
| AI-junior? | Partial |
| Spec refs | architecture.md |

Description. The relational backbone of a conversation flow.

Technical notes

flow_steps: tenant_id FK, label, message_text, is_start, is_terminal, created_at.

flow_options: step_id FK, button_label (max 20 chars), next_step_id FK nullable.

DB constraint: exactly one is_start=true per tenant; null next_step_id = terminal.

Acceptance criteria

☐  button_label > 20 chars is rejected.

☐  A tenant cannot have two start steps (enforced at DB level).

### D1-08 · sessions + messages models

| Tag | [S] Shared |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D1-02 |
| AI-junior? | Yes |
| Spec refs | architecture.md |

Description. Per-conversation state and the message log.

Technical notes

sessions: tenant_id, channel, customer_identifier, current_step_id, status (active|completed|handed_off), started_at, updated_at.

messages: session_id, direction (inbound|outbound), content, channel, sent_at.

Acceptance criteria

☐  A new conversation creates a new session (never reused).

☐  Status enum restricted to the three allowed values.

### D1-09 · audit_logs + auto-record

| Tag | [S] Shared |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D1-05 |
| AI-junior? | NO (SEC-05) |
| Spec refs | CLAUDE.md §7, FR-19 |

Description. Tamper-evident record of every product-owner action.

Technical notes

Model: admin_user_id, action, entity_type, entity_id, diff (JSON), created_at.

Hook admin create/edit/delete to write an audit row automatically.

Acceptance criteria

☐  Every config/flow change lands in audit_logs with actor + timestamp + diff.

### D1-10 · Migrations + constraints check

| Tag | [S] Shared |
| --- | --- |
| Size | S (~½ day) |
| Depends on | D1-05..09 |
| AI-junior? | Yes |
| Spec refs | — |

Description. Lock the schema in with migrations and prove the key constraint.

Technical notes

Generate and apply all migrations.

Acceptance criteria

☐  All migrations apply cleanly.

☐  A test proves the single-start-step constraint holds.

## Epic C — Auth scaffolding (C-06)

### D1-11 · Admin auth (single PO account)

| Tag | [S] Shared |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D1-04 |
| AI-junior? | NO (SEC-05) |
| Spec refs | AP-01 |

Description. Secure the admin surface for the single product-owner user.

Technical notes

JWT or server session; no public registration.

All admin API endpoints reject unauthenticated requests.

Acceptance criteria

☐  Login works for the product-owner account.

☐  Unauthenticated API calls return 401.

### D1-12 · Example DRF endpoint (copy template)

| Tag | [S] Shared |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D1-11 |
| AI-junior? | Yes |
| Spec refs | CLAUDE.md §6 |

Description. A reference vertical slice that Dev 3 copies for every CRUD endpoint.

Technical notes

One resource with serializer + viewset + permission + test.

Document it as the canonical pattern in the repo.

Acceptance criteria

☐  Endpoint passes its test and is documented as the template.

## Epic D — Flow engine (C-03) — stateless, all state in DB

### D1-13 · Session resolver

| Tag | [P] Parallel |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D1-08 |
| AI-junior? | Partial |
| Spec refs | FR-09, flow step 5 |

Description. Find or create the session for an inbound event.

Technical notes

Key on (tenant, channel, customer_identifier).

A new conversation starts a fresh session; no prior data referenced (D-05).

Acceptance criteria

☐  Returning customer restarts from greeting with a new session.

### D1-14 · Current-step renderer

| Tag | [P] Parallel |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D1-07,D1-13 |
| AI-junior? | Partial |
| Spec refs | FR-05/06 |

Description. Turn the session's current step into an outbound message payload.

Technical notes

First inbound message sends the configured greeting before options.

Return step message_text plus its button options.

Acceptance criteria

☐  Greeting precedes options on first contact.

☐  Payload reflects the current step's options.

### D1-15 · Branching / advance

| Tag | [P] Parallel |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D1-14 |
| AI-junior? | NO (core logic) |
| Spec refs | FR-07, flow step 7 |

Description. Advance the session based on which button was tapped.

Technical notes

Match the button reply to a flow_option of the current step.

Set current_step_id to the option's next_step_id.

Acceptance criteria

☐  Tapping a button moves the session to the correct next step.

### D1-16 · Free-text handling

| Tag | [P] Parallel |
| --- | --- |
| Size | S (~½ day) |
| Depends on | D1-14 |
| AI-junior? | Partial |
| Spec refs | FR-08, flow step 6 |

Description. Keep the flow on rails when a customer types free text.

Technical notes

Resend the current step's message + buttons with a short prompt.

Acceptance criteria

☐  Free text never advances or breaks the flow.

### D1-17 · Terminal handling

| Tag | [P] Parallel |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D1-15 |
| AI-junior? | NO (core logic) |
| Spec refs | FR-10/12, flow step 8 |

Description. Decide what happens when a path ends.

Technical notes

Null next_step_id = terminal.

If handoff enabled → emit handoff offer; else send closing message and mark completed.

Acceptance criteria

☐  Terminal with handoff on shows 'Talk to a human'.

☐  Terminal with handoff off sends closing and marks session completed.

### D1-18 · Deleted-step recovery

| Tag | [P] Parallel |
| --- | --- |
| Size | S (~½ day) |
| Depends on | D1-15 |
| AI-junior? | Yes |
| Spec refs | ERR-04 |

Description. Self-heal a session whose step was deleted under it.

Technical notes

Detect current_step_id pointing to a missing step.

Reset to start step, resend greeting, log a recovery event.

Acceptance criteria

☐  Orphaned session recovers to start and logs the event.

### D1-19 · Flow-engine unit tests

| Tag | [P] Parallel |
| --- | --- |
| Size | L (~2 days) |
| Depends on | D1-13..18 |
| AI-junior? | Yes |
| Spec refs | FR-05..10 |

Description. Pin the engine's behaviour with tests across every branch.

Technical notes

Cover greeting, branching, free-text, terminal, recovery.

Acceptance criteria

☐  All flow-engine paths covered and green.

## Epic E — Flow builder (C-07, FR-17) — hardest UI

### D1-20 · Decide live-flow-edit behaviour

| Tag | [D] Dependent |
| --- | --- |
| Size | M (~1 day) |
| Depends on | — |
| AI-junior? | NO |
| Spec refs | D-103, AP-04 |

Description. Decide and document how active sessions behave when a flow is edited. Blocks the builder. Resolves D-103.

Technical notes

Changes take effect on new sessions only (AP-04); define active-session handling.

Acceptance criteria

☐  Behaviour documented in decisions.md; D-103 marked DECIDED.

### D1-21 · Step editor (form-based)

| Tag | [D] Dependent |
| --- | --- |
| Size | L (~2 days) |
| Depends on | D1-20,D1-07 |
| AI-junior? | Partial |
| Spec refs | AP-02 |

Description. Form UI to create and edit steps and mark the start step.

Technical notes

Fields: label + message_text; mark start; no drag-and-drop in v1.

Acceptance criteria

☐  Product owner can create/edit steps and set the start step.

### D1-22 · Option editor

| Tag | [D] Dependent |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D1-21 |
| AI-junior? | Partial |
| Spec refs | AP-02 |

Description. Attach buttons to a step and wire them to next steps.

Technical notes

Add/edit options: button_label + select next step from existing steps.

Acceptance criteria

☐  Options can be added and pointed at any existing step.

### D1-23 · Flow validation gate

| Tag | [D] Dependent |
| --- | --- |
| Size | L (~2 days) |
| Depends on | D1-22 |
| AI-junior? | NO (correctness) |
| Spec refs | AP-03 |

Description. Refuse to activate a structurally invalid flow.

Technical notes

Validate: exactly one start, all next_step_id valid, no orphaned steps.

Acceptance criteria

☐  Invalid flows cannot be activated; the reason is shown.

## Epic F — Handoff backend (C-05)

### D1-24 · Handoff trigger service

| Tag | [D] Dependent |
| --- | --- |
| Size | L (~2 days) |
| Depends on | D1-17,D1-08 |
| AI-junior? | Partial |
| Spec refs | FR-11/13 |

Description. Execute the human-handoff: notify staff, freeze the bot, reassure the customer.

Technical notes

Build payload: customer details, channel, timestamp, conversation path.

Send email (Dev 3 owns the template), mark session handed_off.

Send customer a confirmation, then stop bot responses in that session.

Acceptance criteria

☐  Handoff email sent with full context.

☐  Session marked handed_off and the bot goes silent.

☐  Customer receives a confirmation message.

# Dev 2 — Senior (Integrations)

Scope. Webhook receiver, Meta signature validation, message queue, message sender, WhatsApp 24-hour window, Instagram. Owns the Meta-facing edge and the two open channel decisions (BSP, Instagram capability).

18 tasks across 5 epics.

## Epic A — BSP & Meta setup

### D2-01 · Meta BSP selection

| Tag | [S] Shared |
| --- | --- |
| Size | M (~1 day) |
| Depends on | — |
| AI-junior? | NO |
| Spec refs | WA-01, D-101 |

Description. Choose the WhatsApp Business Solution Provider before any WA work starts; it dictates endpoint format and auth. Resolves D-101.

Technical notes

Compare 360dialog / Twilio / Gupshup on pricing, API, onboarding time.

Note: Meta/BSP onboarding can take 1–2 weeks — start day one.

Acceptance criteria

☐  BSP chosen with rationale; D-101 marked DECIDED.

☐  Sandbox/number access requested.

### D2-02 · Webhook verification (GET challenge)

| Tag | [S] Shared |
| --- | --- |
| Size | S (~½ day) |
| Depends on | D2-01 |
| AI-junior? | Yes |
| Spec refs | WA-04 |

Description. Answer Meta's verification handshake during webhook setup.

Technical notes

Respond to Meta's GET with the hub.challenge value and verify_token check.

Acceptance criteria

☐  Meta successfully verifies the webhook endpoint.

## Epic B — Webhook receiver (C-01)

### D2-03 · Inbound webhook endpoint

| Tag | [S] Shared |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D1-03,D2-02 |
| AI-junior? | Partial |
| Spec refs | C-01, ERR-01 |

Description. Public HTTPS POST endpoint that always answers Meta fast and offloads heavy work.

Technical notes

Always return HTTP 200 to Meta (failures handled internally).

Respond within 5 seconds; all real processing is async.

Acceptance criteria

☐  Endpoint returns 200 in well under 5s regardless of downstream state.

### D2-04 · HMAC-SHA256 signature validation

| Tag | [S] Shared |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D2-03 |
| AI-junior? | NO (SEC-01) |
| Spec refs | FR-03, SEC-01 |

Description. Reject forged webhooks before any processing.

Technical notes

Validate Meta's signature header with HMAC-SHA256 over the raw body.

Invalid → return 200, log, discard (no processing).

Acceptance criteria

☐  Tampered payloads are discarded and logged; valid ones pass.

### D2-05 · Payload extraction

| Tag | [S] Shared |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D2-04 |
| AI-junior? | Yes |
| Spec refs | flow step 2 |

Description. Normalise channel, tenant, customer and message out of Meta's payload.

Technical notes

Extract channel, tenant identifier, customer identifier, message payload.

Handle both WhatsApp and Instagram payload shapes.

Acceptance criteria

☐  A normalised event object is produced for both channels.

### D2-06 · Tenant routing

| Tag | [S] Shared |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D2-05 |
| AI-junior? | Partial |
| Spec refs | FR-04, flow step 3 |

Description. Route each inbound event to the correct tenant.

Technical notes

Look up tenant by destination number / channel identifier.

Not found → log and discard, return 200 immediately.

Acceptance criteria

☐  Events reach the right tenant; unknown destinations are safely dropped.

### D2-07 · Enqueue event

| Tag | [S] Shared |
| --- | --- |
| Size | S (~½ day) |
| Depends on | D2-06 |
| AI-junior? | Yes |
| Spec refs | flow step 4 |

Description. Hand the event to the queue and return.

Technical notes

Push normalised event to Celery; return 200; all further work async.

Acceptance criteria

☐  Event is queued and the request returns 200.

## Epic C — Queue processing (C-02)

### D2-08 · Queue worker → flow engine

| Tag | [P] Parallel |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D2-07,D1-19 |
| AI-junior? | Partial |
| Spec refs | flow steps 5–9 |

Description. Consume queued events and drive the flow engine.

Technical notes

Worker looks up/creates session and calls the flow engine.

Dispatch resulting outbound message to the sender.

Acceptance criteria

☐  An inbound event produces the correct outbound response via the engine.

### D2-09 · Retry + dead-letter policy

| Tag | [P] Parallel |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D2-08 |
| AI-junior? | Partial |
| Spec refs | ERR-02 |

Description. Make processing resilient without dropping messages.

Technical notes

Retry up to 3× with exponential backoff.

After 3 failures → dead-letter queue and alert the product owner.

Acceptance criteria

☐  Transient failures retry; persistent ones dead-letter and alert.

## Epic D — Message sender (C-04)

### D2-10 · Per-tenant sender abstraction

| Tag | [D] Dependent |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D2-08,D1-06 |
| AI-junior? | Partial |
| Spec refs | C-04 |

Description. Send outbound messages via the right Meta API with the right tenant credentials.

Technical notes

Resolve and decrypt per-tenant credentials at send time.

Channel-agnostic interface; channel-specific implementations behind it.

Acceptance criteria

☐  Messages send using the correct tenant's credentials and channel.

### D2-11 · WhatsApp interactive messages

| Tag | [D] Dependent |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D2-10 |
| AI-junior? | Partial |
| Spec refs | WA-02 |

Description. Render WhatsApp reply buttons and list messages within Meta's limits.

Technical notes

Reply buttons ≤ 3 options; list messages ≤ 10; labels ≤ 20 chars.

Auto-select list format when a step exceeds 3 options.

Acceptance criteria

☐  Steps render as buttons or lists per option count, within limits.

### D2-12 · WhatsApp 24-hour window enforcement

| Tag | [D] Dependent |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D2-11 |
| AI-junior? | NO (constraint) |
| Spec refs | WA-03 |

Description. Respect WhatsApp's 24-hour interactive-messaging window.

Technical notes

Check session.updated_at before sending.

If > 23h since last customer message → flag and do NOT send interactive.

v1: do not attempt templates outside the window — just flag and log.

Acceptance criteria

☐  Outside-window interactive sends are blocked, flagged and logged.

### D2-13 · Outbound error handling

| Tag | [D] Dependent |
| --- | --- |
| Size | S (~½ day) |
| Depends on | D2-10 |
| AI-junior? | Yes |
| Spec refs | ERR-03 |

Description. Handle Meta API send errors sanely.

Technical notes

Log all send errors.

Do not retry 4xx; retry once on 5xx.

Acceptance criteria

☐  4xx errors are not retried; 5xx retried once; all logged.

### D2-14 · Outbound message logging

| Tag | [D] Dependent |
| --- | --- |
| Size | S (~½ day) |
| Depends on | D2-10 |
| AI-junior? | Yes |
| Spec refs | flow step 9 |

Description. Persist every outbound message.

Technical notes

Write a messages row (direction=outbound) on each send.

Acceptance criteria

☐  Every sent message is logged with channel and timestamp.

## Epic E — Instagram (IG)

### D2-15 · Instagram capability assessment

| Tag | [S] Shared |
| --- | --- |
| Size | M (~1 day) |
| Depends on | — |
| AI-junior? | NO |
| Spec refs | IG-01, D-102 |

Description. Assess Instagram DM API interactive-message support and report to the product owner for approval. Resolves D-102.

Technical notes

Determine native button/quick-reply support.

If unsupported, propose numbered-text-menu fallback for PO approval.

Acceptance criteria

☐  Findings + recommended UX approved by PO; D-102 marked DECIDED.

### D2-16 · Instagram permissions / OAuth

| Tag | [D] Dependent |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D2-15 |
| AI-junior? | Partial |
| Spec refs | IG-03 |

Description. Connect each tenant's Instagram account with the needed scopes.

Technical notes

Grant instagram_manage_messages and pages_messaging via Meta OAuth.

Requires a linked Facebook Page per tenant.

Acceptance criteria

☐  A tenant's IG account can send/receive messages through the platform.

### D2-17 · Instagram renderer / fallback

| Tag | [D] Dependent |
| --- | --- |
| Size | L (~2 days) |
| Depends on | D2-16,D2-12 |
| AI-junior? | Partial |
| Spec refs | IG-02 |

Description. Render flows on Instagram, using the approved fallback if buttons are unavailable.

Technical notes

If no buttons: parse '1'/'2'/'3' as option selections — Instagram only.

Must not change WhatsApp logic.

Acceptance criteria

☐  IG sessions navigate the flow via the approved UX.

☐  WhatsApp behaviour is unaffected.

### D2-18 · Channel integration tests

| Tag | [D] Dependent |
| --- | --- |
| Size | L (~2 days) |
| Depends on | D2-17,D2-14 |
| AI-junior? | Yes |
| Spec refs | FR-01..04 |

Description. Prove inbound→outbound works on both channels.

Technical notes

Simulated webhook → engine → sender for WhatsApp and Instagram.

Acceptance criteria

☐  End-to-end channel tests pass for both WhatsApp and Instagram.

# Dev 3 — Junior (Admin & Config)

Scope. Admin CRUD, per-client config screens, conversation-log viewer, handoff email content, seed/test data, onboarding runbook. Low blast-radius, screen-verifiable work; security and flow-state logic stay with the Seniors.

11 tasks across 4 epics.

## Epic A — Admin CRUD & config

### D3-01 · Tenant create / edit / deactivate

| Tag | [P] Parallel |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D1-05,D1-12 |
| AI-junior? | Yes |
| Spec refs | FR-15, AP-01 |

Description. Let the product owner manage business-client accounts.

Technical notes

Fields: name, WA number, Instagram account ID, handoff email, active status.

Build on Django admin / the D1-12 endpoint template.

Acceptance criteria

☐  PO can create, edit and deactivate a client.

☐  Deactivated clients are clearly marked.

### D3-02 · Per-client config screens

| Tag | [P] Parallel |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D3-01 |
| AI-junior? | Yes |
| Spec refs | FR-16 |

Description. Expose the per-client conversational settings.

Technical notes

Edit greeting message, closing message, handoff toggle, handoff email.

Acceptance criteria

☐  Each setting saves and is reflected by the bot's behaviour.

### D3-03 · Config validation

| Tag | [P] Parallel |
| --- | --- |
| Size | S (~½ day) |
| Depends on | D3-02 |
| AI-junior? | Yes |
| Spec refs | FR-16 |

Description. Prevent obviously broken configs.

Technical notes

Require handoff_email when handoff is enabled; validate email format.

Acceptance criteria

☐  Enabling handoff without a valid email is blocked with a clear message.

## Epic B — Conversation logs

### D3-04 · Conversation-log viewer

| Tag | [P] Parallel |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D1-08 |
| AI-junior? | Yes |
| Spec refs | FR-18 |

Description. Read-only view of message history per client.

Technical notes

List messages with direction, channel and timestamps, filterable by tenant.

Read-only — no editing.

Acceptance criteria

☐  PO can browse a client's message history with timestamps and channel.

### D3-05 · Path-taken display

| Tag | [P] Parallel |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D3-04 |
| AI-junior? | Partial |
| Spec refs | FR-18 |

Description. Show the sequence of steps a session walked.

Technical notes

Reconstruct and display the ordered path for a session.

Acceptance criteria

☐  A session's button path is visible end-to-end.

### D3-06 · Audit-log viewer

| Tag | [P] Parallel |
| --- | --- |
| Size | S (~½ day) |
| Depends on | D1-09 |
| AI-junior? | Yes |
| Spec refs | FR-19 |

Description. Surface the audit trail for review.

Technical notes

Read-only list of audit_logs with actor, action, entity, timestamp.

Acceptance criteria

☐  Admin actions are reviewable in a read-only audit view.

## Epic C — Handoff content

### D3-07 · Handoff email template

| Tag | [D] Dependent |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D1-24 |
| AI-junior? | Yes |
| Spec refs | FR-11 |

Description. Author the email the human agent receives on handoff.

Technical notes

Include customer details, channel, timestamp, conversation path.

Plain, scannable layout; no customer PII beyond what's needed.

Acceptance criteria

☐  Handoff email is clear, complete and renders in common clients.

### D3-08 · Customer confirmation message

| Tag | [D] Dependent |
| --- | --- |
| Size | S (~½ day) |
| Depends on | D1-24 |
| AI-junior? | Yes |
| Spec refs | FR-13 |

Description. Write the message the customer sees after requesting a human.

Technical notes

Reassure them a human will follow up; set expectations.

Acceptance criteria

☐  Confirmation copy approved and wired into the handoff flow.

## Epic D — Fixtures & enablement

### D3-09 · Demo seed data

| Tag | [P] Parallel |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D1-10 |
| AI-junior? | Yes |
| Spec refs | architecture.md |

Description. A realistic demo tenant to develop and demo against.

Technical notes

One tenant + a sample flow: greeting → two branches → terminal.

Acceptance criteria

☐  A single command seeds a working demo tenant and flow.

### D3-10 · Test fixtures / factories

| Tag | [P] Parallel |
| --- | --- |
| Size | M (~1 day) |
| Depends on | D1-10 |
| AI-junior? | Yes |
| Spec refs | — |

Description. Reusable factories so every dev's tests have data.

Technical notes

factory-boy factories for tenants, flows, steps, options, sessions.

Acceptance criteria

☐  Other devs can build test objects from shared factories.

### D3-11 · Client onboarding runbook

| Tag | [P] Parallel |
| --- | --- |
| Size | S (~½ day) |
| Depends on | D3-02 |
| AI-junior? | Yes |
| Spec refs | FR-15/16 |

Description. A short guide the product owner follows to onboard a client.

Technical notes

Step-by-step: create tenant, enter credentials, set messages, build flow, go live.

Acceptance criteria

☐  A non-engineer can onboard a client by following the runbook.